## Corrected Schedule
Task ID | WBS | Task | Phase | Workstream | Owner | Duration (days) | Start | Finish | Predecessors | Successors | Deliverable | Milestone
EMS-001 | 1.1.1 | Confirm NEC/RAH objectives and EMS success criteria | Initiation and planning | Governance | Project Director | 5 | 2025-07-15 | 2025-07-20 | - | 1.1.2 | Approved business objectives and MOV | No
EMS-002 | 1.1.2 | Map stakeholders and communication needs | Initiation and planning | Stakeholder management | Project Director | 7 | 2025-07-20 | 2025-07-27 | 1.1.1 | 1.1.3 | Stakeholder register and communication matrix | No
EMS-003 | 1.1.3 | Define EMS project charter | Initiation and planning | Governance | Project Director | 8 | 2025-07-27 | 2025-08-04 | 1.1.2 | 1.2.1 | Project charter | No
EMS-004 | 1.2.1 | Create scope baseline for registration, ticketing, schedule, budget, and security modules | Initiation and planning | Scope | System Architect | 10 | 2025-08-04 | 2025-08-14 | 1.1.3 | 1.2.2 | Scope statement and exclusions | No
EMS-005 | 1.2.2 | Develop WBS dictionary and acceptance criteria | Initiation and planning | Scope | Scrum Master / Agile Coach | 7 | 2025-08-14 | 2025-08-21 | 1.2.1 | 1.3.1 | WBS dictionary | No
EMS-006 | 1.3.1 | Build risk, quality, procurement, and change-control plans | Initiation and planning | Controls | Operations Manager | 12 | 2025-08-21 | 2025-09-02 | 1.2.2 | 1.4.1 | Integrated management control plan | No
EMS-007 | 1.4.1 | Baseline budget and resource plan within AUD 1.5M cap | Initiation and planning | Cost and resources | Project Director | 8 | 2025-09-02 | 2025-09-10 | 1.3.1 | 1.5.1 | Budget and resource baseline | No
M-008 | 1.5.1 | Milestone: planning baseline approved | Initiation and planning | Milestone | PMP Steering Group | 0 | 2025-09-10 | 2025-09-10 | 1.4.1 | 2.1.1 | Planning sign-off | Yes
EMS-009 | 2.1.1 | Define EMS solution architecture and integration map | Design and development | Architecture | System Architect | 15 | 2025-09-10 | 2025-09-25 | 1.5.1 | 2.1.2, 2.1.3 | Architecture baseline | No
EMS-010 | 2.1.2 | Design data model, privacy controls, and cybersecurity architecture | Design and development | Architecture | System Architect | 12 | 2025-09-25 | 2025-10-07 | 2.1.1 | 2.2.1, 2.2.3, 2.2.4, 2.2.5 | Security and data design | No
EMS-011 | 2.1.3 | Prepare UI/UX prototypes for attendee, vendor, staff, and NEC admin flows | Design and development | Experience design | UI/UX Designer | 20 | 2025-09-25 | 2025-10-15 | 2.1.1 | 2.2.1, 2.2.3 | Prototype set | No
EMS-012 | 2.2.1 | Build online registration module | Design and development | Core platform | Frontend Developer | 35 | 2025-10-15 | 2025-11-19 | 2.1.2, 2.1.3 | 2.2.2 | Registration workflow | No
EMS-013 | 2.2.2 | Build ticketing, payment, QR/RFID validation, and entry scanning module | Design and development | Core platform | Ticketing System Specialist | 70 | 2025-11-19 | 2026-01-28 | 2.2.1 | 2.3.1 | Ticketing and access-control workflow | No
EMS-014 | 2.2.3 | Build performance scheduling and rehearsal management module | Design and development | Core platform | Backend Developer | 45 | 2025-10-15 | 2025-11-29 | 2.1.2, 2.1.3 | 2.3.1 | Schedule management workflow | No
EMS-015 | 2.2.4 | Build budget analytics dashboard and reporting views | Design and development | Analytics | Database Administrator | 40 | 2025-10-07 | 2025-11-16 | 2.1.2 | 2.3.1 | Budget analytics module | No
EMS-016 | 2.2.5 | Build security management dashboard and incident reporting workflow | Design and development | Security | Cybersecurity Engineer | 55 | 2025-10-07 | 2025-12-01 | 2.1.2 | 2.3.1 | Security dashboard | No
EMS-017 | 2.3.1 | Integrate vendor APIs, mobile app views, and NEC admin portal | Design and development | Integration | API Engineer | 40 | 2026-01-28 | 2026-03-09 | 2.2.2, 2.2.3, 2.2.4, 2.2.5 | 2.4.1 | Integrated EMS platform | No
EMS-018 | 2.4.1 | Complete internal sprint reviews and defect triage | Design and development | Quality | Scrum Master / Agile Coach | 20 | 2026-03-09 | 2026-03-29 | 2.3.1 | 2.5.1 | Sprint review pack | No
M-019 | 2.5.1 | Milestone: integrated EMS build complete | Design and development | Milestone | PMP Steering Group | 0 | 2026-03-29 | 2026-03-29 | 2.4.1 | 3.1.1 | Build completion sign-off | Yes
EMS-020 | 3.1.1 | Run system integration testing across all EMS modules | Testing and validation | Testing | QA Test Engineer | 35 | 2026-03-29 | 2026-05-03 | 2.5.1 | 3.1.2, 3.1.3 | SIT report | No
EMS-021 | 3.1.2 | Run security, privacy, and penetration testing | Testing and validation | Security testing | Security Tester | 25 | 2026-05-03 | 2026-05-28 | 3.1.1 | 3.2.1 | Security test report | No
EMS-022 | 3.1.3 | Run performance, load, and entry-scanning stress testing | Testing and validation | Performance testing | Performance Test Engineer | 20 | 2026-05-03 | 2026-05-23 | 3.1.1 | 3.2.1 | Load-test report | No
EMS-023 | 3.2.1 | Conduct NEC staff UAT and festival operations rehearsal | Testing and validation | User acceptance | Operations Manager | 25 | 2026-05-28 | 2026-06-22 | 3.1.2, 3.1.3 | 3.2.2 | UAT sign-off log | No
EMS-024 | 3.2.2 | Resolve priority defects and update training materials | Testing and validation | Defect remediation | Scrum Master / Agile Coach | 20 | 2026-06-22 | 2026-07-12 | 3.2.1 | 3.3.1 | Defect closure and training pack | No
M-025 | 3.3.1 | Milestone: EMS validated for deployment | Testing and validation | Milestone | PMP Steering Group | 0 | 2026-07-12 | 2026-07-12 | 3.2.2 | 4.1.1 | Deployment approval | Yes
EMS-026 | 4.1.1 | Prepare cloud production environment and monitoring | Deployment and readiness | Release | DevOps Engineer | 20 | 2026-07-12 | 2026-08-01 | 3.3.1 | 4.1.2 | Production environment | No
EMS-027 | 4.1.2 | Migrate configuration, event data, ticket templates, and vendor records | Deployment and readiness | Release | Database Administrator | 15 | 2026-08-01 | 2026-08-16 | 4.1.1 | 4.2.1 | Migration checklist | No
EMS-028 | 4.2.1 | Train NEC operations, security, ticketing, and vendor-support users | Deployment and readiness | Training | Operations Manager | 25 | 2026-08-16 | 2026-09-10 | 4.1.2 | 4.3.1 | Training completion register | No
EMS-029 | 4.3.1 | Run production pilot and go-live rehearsal | Deployment and readiness | Release | Project Director | 20 | 2026-09-10 | 2026-09-30 | 4.2.1 | 4.4.1 | Pilot readiness report | No
EMS-030 | 4.4.1 | Operate final contingency and defect-remediation window | Deployment and readiness | Controls | PMP Delivery Team | 45 | 2026-09-30 | 2026-11-14 | 4.3.1 | 4.5.1 | Readiness reserve log | No
M-031 | 4.5.1 | Milestone: EMS ready for 2027 Sydney Festival operations | Deployment and readiness | Milestone | NEC Sponsor | 0 | 2026-11-14 | 2026-11-14 | 4.4.1 | 5.1.1 | Operational readiness sign-off | Yes
EMS-032 | 5.1.1 | Complete handover, lessons learned, and support transition | Closeout | Handover | Project Director | 10 | 2026-11-14 | 2026-11-24 | 4.5.1 | 5.2.1 | Handover pack | No
EMS-033 | 5.2.1 | Archive project evidence and final management report | Closeout | Reporting | Scrum Master / Agile Coach | 6 | 2026-11-24 | 2026-11-30 | 5.1.1 | 5.3.1 | Final report archive | No
M-034 | 5.3.1 | Milestone: PMP final submission complete | Closeout | Milestone | PMP Steering Group | 0 | 2026-11-30 | 2026-11-30 | 5.2.1 | - | Final submission sign-off | Yes

## WBS Summary
WBS | Work Package | Description
1 | Initiation and planning | Define governance, scope, stakeholders, controls, budget, and delivery baseline.
2 | Design and development | Design and build the integrated EMS platform modules.
3 | Testing and validation | Validate the EMS through system, security, performance, and UAT activities.
4 | Deployment and readiness | Prepare production, migrate configuration, train users, and confirm operational readiness.
5 | Closeout | Handover the project and archive final evidence.

## Validation Notes
Check | Finding | Correction
Required finish date | Original detailed Gantt ended on 2028-04-25. | Corrected baseline finishes on 2026-11-30, matching the report constraint.
Milestones | 8 original milestone rows had positive durations. | Corrected milestones use 0-day duration.
WBS workbook readability | Original WBS workbook used a strict OOXML namespace that common parsers failed to expose as a normal sheet. | Recovered source rows and created readable corrected CSV/XLSX outputs.
Duplicate wording | Duplicate titles found: Develop project charter, Define project scope statement. | Corrected schedule uses unique activity names.